## Sheet1
2012-07-30 | Organize, start basic environment
2012-07-31 | Dummy fish are loaded and move around
2012-08-01 | Other objects are coded to interact
2012-08-02 | Interface, scores
2012-08-03 | Joystick inputs work to move player
2012-08-04 | Player interaction working decently
2012-08-05 | Player interaction working well with all game aspects
2012-08-06 | By the end of the day have a decently working game
2012-08-07 | Touch up the game, fix bugs
2012-08-08 | Have a finished game, just very minor flaws
2012-08-09 | Finish off all game aspects
2012-08-10 | DONE